## Application
Iowa Nurse Connect – Iowa Hospital Association Project Estimated Plan
Stage Serial Number | Milestones | Comments/Queries | Estimated Hours
1 | Preparation of Detailed Design Document
| Requirements Gathering, Analysis& Clarification | This will be an ongoing process will be achieved parallel to the other milestones but at the initial stage these tasks will take the mentioned time.
Total Hours
2 | Application Development
Please note** The estimates for the steps mentioned below are subject to change and will be revised after the Requirement Analysis phase.
3
Operations
| 1. Admin Panel |  | 145
Admin Dashboard
User Management (ADD/Edit/Delete)
Role Management (ADD/Edit/Delete)
College Management (ADD/Edit/Delete)
Reports (ADD/Edit/Delete)
MFA authentication
Print Save Reports
| 2. College Content Manager |  | 155
College Content Management
Degree Management (ADD/Edit/Delete)
Pragramme Management (ADD/Edit/Delete)
Term Management (ADD/Edit/Delete)
Manage Downloadable Material/Content
College Recuriters Management (ADD/Edit/Delete)
| 3. Student Portal |  | 55
Login/Sign up
Dashboard
Listing intrested Pragramme /college/
MFA Authentication
College Filteration
| 4. College Recuiters |  | 40
Dashboard
Manage Recuits/Status
Reports
| 5. Public Pages |  | 150
Home
Carrer in Nursing
Contact US
College Listing - Filteration
Programme listing - Filteration
College Details Page
Pragramme Details Page
Apply for Programme
Login/Forget Password
Sign up
ChatBot
FAQ
Design /Mockups
5 | Testing (QA) and Bug fixing
| Unit testing, Regression testing |  | 60
6 | Application Deployment on production site (Non Billable)
| Deployment and configuration setup. |  | 10
7 | Enhacement Scope
| Total HRS |  | 615